STATEMENT OF WORK TEMPLATE

Template Version: 1.0

Document Type: Generic Statement of Work

Effective Date: January 18, 2024

================================================================================

METADATA TABLE

Contract Type: Statement of Work (SOW)

Vendor: Generic

Effective Date: January 18, 2024

Client: GlobalTech Inc

Project Code: GT-CM-2024-002

Document Version: 1.0

Last Updated: January 15, 2024

Prepared By: Amanda Foster

Approved By: Robert Martinez

================================================================================

1. PROJECT OVERVIEW

This Statement of Work ("SOW") sets forth the terms and conditions under which DataFlow Solutions ("Vendor") will provide services to GlobalTech Inc ("Client") for the Cloud Migration Project project. This SOW is governed by the Master Services Agreement between the parties dated November 15, 2023 and incorporates all terms and conditions contained therein.

The project objective is to migrate GlobalTech's on-premises infrastructure to AWS cloud platform while ensuring minimal downtime and enhanced security posture. The Vendor shall provide professional services including but not limited to infrastructure assessment, cloud architecture design, migration execution, and security implementation in accordance with the specifications, timelines, and deliverables outlined in this document.

This engagement is expected to commence on January 18, 2024 and conclude on September 18, 2024, subject to the terms and conditions set forth herein. The total estimated value of this engagement is $420,000 as detailed in the payment terms section.

2. SCOPE OF WORK

The Vendor shall perform the following services and activities:

2.1 Primary Services

DataFlow Solutions shall provide cloud migration and infrastructure services including but not limited to:

- Current infrastructure assessment and cloud readiness evaluation

- AWS cloud architecture design and security planning

- Application migration and modernization services

- Network configuration and security implementation

2.2 Secondary Services

Additional services may include:

- Performance monitoring and optimization setup

- Disaster recovery planning and implementation

- Staff training on cloud operations and management

- 60-day post-migration support and optimization

2.3 Exclusions

The following items are specifically excluded from this SOW:

- AWS service costs and licensing fees

- Legacy system decommissioning

- Data archival beyond migration requirements

Any services not explicitly included in this SOW shall require a separate written agreement or change order as outlined in Section 9.

3. DELIVERABLES

The Vendor shall provide the following deliverables according to the specified timeline:

3.1 Phase 1 Deliverables

- Infrastructure Assessment Report: Detailed analysis of current environment - Due: February 18, 2024

- Cloud Architecture Blueprint: AWS design and migration strategy - Due: March 5, 2024

- Security Framework Document: Cloud security implementation plan - Due: March 20, 2024

3.2 Phase 2 Deliverables

- Migrated Core Systems: Production workloads in AWS environment - Due: June 15, 2024

- Network Security Implementation: Configured firewalls and access controls - Due: July 1, 2024

3.3 Final Deliverables

- Complete Cloud Environment: Fully operational AWS infrastructure - Due: August 30, 2024

- Operations Documentation: Comprehensive management and monitoring guides - Due: September 18, 2024

All deliverables shall be provided in the format specified by the Client and shall meet the acceptance criteria outlined in Section 6.

4. PROJECT TIMELINE

The project shall be executed according to the following timeline:

Phase 1: Project Initiation (January 18, 2024 - March 20, 2024)

- Week 1-2: Project kickoff and requirements gathering

- Week 3-4: Initial analysis and planning

- Week 5-6: Architecture design and security planning

Phase 2: Implementation (March 21, 2024 - July 1, 2024)

- Week 7-10: Infrastructure setup and initial migrations

- Week 11-12: Testing and validation

- Week 13-14: Security implementation and hardening

Phase 3: Project Closure (July 2, 2024 - September 18, 2024)

- Week 15-16: Final deliverables and handover

- Week 17-18: Project closure and knowledge transfer

Key milestones include:

- Architecture Approval: March 20, 2024

- First System Migration: May 15, 2024

- Production Cutover: August 30, 2024

5. RESOURCE ALLOCATION

5.1 Vendor Resources

The Vendor shall assign the following resources to this project:

- Project Manager: Carlos Mendez - 25 hours/week

- Technical Lead: Patricia Lee - 35 hours/week

- Senior Consultant: Mark Stevens - 40 hours/week

- Junior Consultant: Emily Chen - 25 hours/week

5.2 Client Resources

The Client shall provide the following resources:

- Project Sponsor: Robert Martinez

- Business Analyst: Amanda Foster

- Technical Contact: Kevin O'Brien

- End User Representatives: IT Operations Team

5.3 Resource Responsibilities

All Vendor resources shall be qualified professionals with appropriate experience and certifications. The Vendor shall ensure adequate resource availability throughout the project duration and shall notify the Client immediately of any resource changes.

6. ACCEPTANCE CRITERIA

6.1 Deliverable Acceptance

Each deliverable shall be subject to Client review and acceptance. The Client shall have 7 business days from receipt to review and either accept or reject each deliverable with specific written feedback.

6.2 Acceptance Process

- Vendor submits deliverable with completion notice

- Client reviews deliverable against specified criteria

- Client provides written acceptance or rejection with detailed feedback

- If rejected, Vendor has 5 business days to address issues

- Process repeats until deliverable is accepted

6.3 Acceptance Criteria Standards

All deliverables must meet the following minimum standards:

- Completeness according to specifications

- Quality standards as defined in project requirements

- Compliance with applicable regulations and standards

- Documentation requirements as specified

7. ASSUMPTIONS AND DEPENDENCIES

7.1 Assumptions

This SOW is based on the following assumptions:

- Current infrastructure documentation is complete and accurate

- AWS account setup and initial credits are available

- Network connectivity requirements can be met

- Existing applications are cloud-compatible or can be modernized

7.2 Dependencies

Project success is dependent upon:

- Timely provision of Client resources and information

- Access to required systems and environments

- AWS service availability and performance

- Client approval of security configurations

- Coordination with existing vendor contracts

7.3 Risk Mitigation

The parties acknowledge that changes to assumptions or dependencies may impact project scope, timeline, or cost and agree to address such changes through the change management process outlined in Section 9.

8. PAYMENT TERMS

8.1 Total Contract Value

The total value of this engagement is $420,000 payable according to the schedule below.

8.2 Payment Schedule

- Phase 1 Completion: $150,000 due within 30 days of acceptance

- Phase 2 Completion: $200,000 due within 30 days of acceptance

- Final Deliverables: $70,000 due within 30 days of project completion

8.3 Invoicing

The Vendor shall submit invoices monthly for work completed. All invoices shall include:

- Detailed description of work performed

- Hours worked by resource type

- Deliverables completed

- Project code reference: GT-CM-2024-002

Payment terms are Net 30 days from receipt of properly submitted invoice.

8.4 Expenses

Pre-approved expenses shall be reimbursed at cost with appropriate documentation. Travel expenses require prior written approval from the Client.

9. CHANGE MANAGEMENT

9.1 Change Request Process

Any changes to this SOW must be documented through a formal change request process including:

- Written description of proposed change

- Impact analysis on scope, timeline, and cost

- Client approval before implementation

- Updated SOW documentation

9.2 Change Authorization

Changes exceeding $15,000 require written approval from Robert Martinez. Minor changes may be approved by the designated project manager.

9.3 Change Implementation

Approved changes shall be implemented according to revised timeline and specifications. No work on changes shall commence without proper authorization.

10. TERMS AND CONDITIONS

10.1 Governing Agreement

This SOW is governed by the Master Services Agreement between the parties dated November 15, 2023. In case of conflict, the MSA shall take precedence.

10.2 Confidentiality

Both parties acknowledge that confidential information may be exchanged during this engagement and agree to maintain strict confidentiality according to the terms of the MSA.

10.3 Intellectual Property

All work product created under this SOW shall be owned by the Client upon full payment. The Vendor retains rights to general methodologies and know-how.

10.4 Limitation of Liability

The Vendor's liability under this SOW shall not exceed the total value of the contract. Neither party shall be liable for indirect, consequential, or punitive damages.

10.5 Termination

Either party may terminate this SOW with 45 days written notice. Upon termination, the Vendor shall be compensated for work completed and accepted.

10.6 Force Majeure

Neither party shall be liable for delays or failures due to circumstances beyond their reasonable control including but not limited to acts of God, government actions, or natural disasters.

================================================================================

SIGNATURE BLOCK

CLIENT: GlobalTech Inc

By: _________________________    Date: ___________

Name: Robert Martinez

Title: Chief Information Officer

VENDOR: DataFlow Solutions

By: _________________________    Date: ___________

Name: Carlos Mendez

Title: Project Manager

================================================================================

Document Control:

Template ID: TYPE_SOW_Standard_v1

Version: 1.0

Created: January 15, 2024

Last Modified: January 15, 2024

Next Review: September 18, 2024